UNIT–2 AGILE MINI PROJECT

Enterprise Student Record and
Academic Management Platform

Agile Project Planning, Scrum Execution and Release Documentation

| Project Information | Details |
| --- | --- |
| Student Name | Omkar Dnyaneshwar Ghorpade |
| PRN / Roll No. | 2125UDSM1033 |
| Branch / Class | AIDS |
| Faculty / Trainer | Mr. Karan Gaikwaad Sir |
| Academic Unit | Unit 2 – Agile Project Planning |
| Project Type | Training & Technical Mini Project |

# Table of Contents

1. Executive Summary and Unit-1 Project Continuity

2. Study of the Business Problem and Product Vision

3. Agile Product Vision

4. Scrum Team Structure and Roles

5. Project Epics

6. User Story Repository

7. Acceptance Criteria and Definition of Done

8. Prioritized Product Backlog

9. Story Point Estimation

10. Sprint Planning

11. Sprint Backlogs

12. Scrum Board Development

13. Burndown Chart and Sprint Progress

14. Simulated Scrum Ceremonies

15. Sprint Review Report

16. Sprint Retrospective Report

17. Comparative Study of Agile Frameworks

18. Project Timeline and Release Roadmap

19. Complete Agile Documentation Summary

20. Conclusion and Submission Checklist

# 1. Executive Summary and Unit-1 Project Continuity

This Unit-2 Agile Mini Project continues the Enterprise Student Record and Academic Management Platform developed during Unit 1. Unit 1 established the business problem, stakeholder needs, user personas, functional and non-functional requirements, product vision, MVP scope, initial architecture and product roadmap. Unit 2 converts that product-discovery work into an executable Agile development plan.

The central business problem remains the same: higher-education institutions often depend on manual files, disconnected spreadsheets and separate academic workflows. This creates delays, duplicate records, calculation mistakes and limited visibility. The proposed platform centralizes student registration, course management, attendance, marks, results, notifications and reporting through secure role-based access.

| Unit 1 Output | How It Is Used in Unit 2 |
| --- | --- |
| Business Problem | Provides the reason and value for prioritizing Agile features. |
| Stakeholders and Personas | Help define users and write user-centered stories. |
| FRS and NFRS | Become the source for Epics, User Stories and Acceptance Criteria. |
| Product Vision and Mission | Guide the Agile Product Vision and Sprint Goals. |
| MVP Scope | Identifies the highest-priority backlog items. |
| Product Roadmap | Provides the foundation for release planning. |
| Initial Architecture | Supports technical planning and implementation dependencies. |

Therefore, Unit 2 does not create a different product. It plans the same product using Scrum and Agile practices so that development can happen incrementally and each Sprint delivers meaningful value.

# 2. Study of the Business Problem and Product Vision

## 2.1 Business Problem

Academic institutions need a centralized and reliable way to manage student information. Manual and disconnected processes make registration, attendance, examination management and report generation slower and more error-prone. Different stakeholders also need different levels of access, which makes security and information governance important.

## 2.2 Key Stakeholders

| Stakeholder | Primary Need | Agile Value Expected |
| --- | --- | --- |
| Students | Fast access to attendance, courses and results | Transparent self-service information |
| Faculty Members | Simple attendance and marks entry | Less repetitive calculation and data entry |
| Academic Administrators | Centralized records and reports | Better visibility and control |
| Examination Cell | Accurate marks and controlled results | Reliable processing and auditability |
| IT Support | Maintainable and secure application | Easier monitoring, backup and support |
| Management | Useful academic summaries | Better institutional decision support |

## 2.3 Product Scope Used for Agile Planning

Authentication and role-based access control

Student registration and profile management

Course registration and course management

Attendance recording and attendance reports

Marks entry and academic performance processing

Result generation and publication

Notifications for important academic events

Student, attendance, performance and course reporting

The Agile plan gives priority to the MVP features first. Advanced analytics, AI recommendations, external payment integrations and large third-party integrations remain outside the first release.

# 3. Agile Product Vision

## 3.1 Agile Product Vision Statement

"Develop a secure, scalable and user-friendly Student Record and Academic Management Platform that enables educational institutions to manage student records, course enrollment, attendance, marks, results, notifications and reporting through incremental, feedback-driven Agile development."

## 3.2 Overall Product Objective

The objective is to replace fragmented academic workflows with one trusted digital platform while delivering the highest-value capabilities first through short, measurable development Sprints.

## 3.3 Primary Users

| Primary User | Main Outcome |
| --- | --- |
| Student | View authorized academic information and track progress. |
| Faculty | Record attendance and marks efficiently. |
| Administrator | Manage records and generate institutional reports. |
| Examination Staff | Process marks and publish approved results. |
| IT Support | Maintain a secure and reliable system. |

## 3.4 Business Benefits

Reduced manual administrative effort

Improved record accuracy and consistency

Faster access to academic information

Reduced calculation and transcription errors

Role-based protection of sensitive records

Incremental delivery with early user feedback

## 3.5 Measurable Success Criteria

| Success Area | Measure |
| --- | --- |
| Usability | Common tasks can be completed through clear and simple workflows. |
| Accuracy | Validation reduces duplicate records and incorrect calculations. |
| Efficiency | Routine academic tasks and reports require less manual effort. |
| Security | Only authorized roles can access protected functions and data. |
| Sprint Delivery | Selected Sprint backlog items meet agreed acceptance criteria. |
| Quality | Completed stories are tested before being marked Done. |

## 3.6 Project Constraints

Limited development time for a mini-project environment

Small Scrum team and limited resources

Dependencies between modules such as students, courses and attendance

Need to protect academic data and maintain role-based access

MVP-first scope to prevent uncontrolled feature expansion

# 4. Scrum Team Structure and Roles

For this academic mini project, the Scrum structure is simulated clearly so that responsibilities are visible even when the project is completed by a small student team.

| Scrum Role | Assigned Responsibility | Key Activities |
| --- | --- | --- |
| Product Owner | Represents stakeholder and product needs | Prioritizes backlog, clarifies requirements, accepts completed work |
| Scrum Master | Supports the Scrum process | Facilitates ceremonies, removes impediments, improves collaboration |
| Development Team | Builds the product incrementally | Designs, codes, tests, documents and demonstrates features |

## 4.1 Product Owner Responsibilities

Maintain and prioritize the Product Backlog.

Ensure User Stories reflect stakeholder and MVP needs.

Clarify requirements and acceptance criteria.

Accept or reject work based on the Definition of Done.

## 4.2 Scrum Master Responsibilities

Conduct Sprint Planning, Daily Scrum, Sprint Review and Retrospective.

Track impediments and help the team resolve them.

Ensure the Scrum Board is updated.

Encourage continuous improvement.

## 4.3 Development Team Responsibilities

Convert selected User Stories into working software.

Perform design, implementation and testing.

Maintain documentation and repository history.

Demonstrate completed work during Sprint Review.

# 5. Project Epics

Epics are high-level functional groups that organize the complete application before they are broken into smaller User Stories.

| Epic ID | Epic | Purpose |
| --- | --- | --- |
| E1 | Authentication and Security | Provide secure login, logout, password recovery and role-based access. |
| E2 | Student Management | Create, search, update, view and maintain student profiles. |
| E3 | Course Management | Create and manage courses and semester-wise student enrollment. |
| E4 | Attendance Management | Record attendance, calculate percentages and generate attendance information. |
| E5 | Marks and Academic Performance | Enter, update and validate marks and calculate academic grades/results. |
| E6 | Notifications | Inform users about attendance, examinations and published results. |
| E7 | Reporting | Generate student, attendance, performance and course reports. |

## 5.1 Epic Scope

### E1 – Authentication and Security

Provide secure login, logout, password recovery and role-based access.

User login

User logout

Password reset

Role-based access control

### E2 – Student Management

Create, search, update, view and maintain student profiles.

Student registration

Student profile view

Search student

Update student information

### E3 – Course Management

Create and manage courses and semester-wise student enrollment.

Add course

Update course

Assign students to courses

View course details

### E4 – Attendance Management

Record attendance, calculate percentages and generate attendance information.

Record attendance

View attendance

Calculate attendance percentage

Attendance reports

### E5 – Marks and Academic Performance

Enter, update and validate marks and calculate academic grades/results.

Enter marks

Update marks

Calculate grades

Generate result sheet

### E6 – Notifications

Inform users about attendance, examinations and published results.

Attendance alerts

Examination notifications

Result notifications

### E7 – Reporting

Generate student, attendance, performance and course reports.

Student reports

Attendance reports

Performance reports

Course reports

# 6. User Story Repository

Each User Story follows the format: As a <user>, I want <capability>, so that <benefit>. The stories below are directly aligned with the Unit-1 requirements and Unit-2 Agile scope.

| ID | Epic | User Story | Priority |
| --- | --- | --- | --- |
| US-01 | E1 | As a registered user, I want to log in using valid credentials so that I can access my authorized dashboard. | High |
| US-02 | E1 | As a user, I want to log out securely so that my session is protected when I finish using the system. | High |
| US-03 | E1 | As a user, I want to reset my password securely so that I can regain access when I forget it. | Medium |
| US-04 | E1 | As an administrator, I want role-based access control so that users can access only authorized functions. | High |
| US-05 | E2 | As an administrator, I want to register a student so that a centralized academic profile can be created. | High |
| US-06 | E2 | As an authorized user, I want to search for a student so that I can quickly locate required academic records. | High |
| US-07 | E2 | As an administrator, I want to update student information so that records remain accurate. | Medium |
| US-08 | E2 | As a student, I want to view my profile so that I can check my authorized academic information. | Medium |
| US-09 | E3 | As an administrator, I want to add a course so that academic offerings can be maintained digitally. | Medium |
| US-10 | E3 | As an administrator, I want to assign students to courses so that semester enrollment is recorded. | High |
| US-11 | E3 | As an authorized user, I want to view course details so that I can understand course information. | Medium |
| US-12 | E4 | As a faculty member, I want to record student attendance so that attendance records remain accurate and updated. | High |
| US-13 | E4 | As a student, I want to view my attendance percentage so that I can monitor my academic eligibility. | High |
| US-14 | E4 | As an administrator, I want attendance reports so that attendance patterns can be reviewed. | Medium |
| US-15 | E5 | As a faculty member, I want to enter student marks so that academic performance can be recorded. | High |
| US-16 | E5 | As authorized examination staff, I want to update approved marks so that corrected records remain accurate. | Medium |
| US-17 | E5 | As examination staff, I want the system to calculate grades so that result processing is consistent. | High |
| US-18 | E5 | As a student, I want to view my approved result so that I can know my academic performance. | High |
| US-19 | E6 | As a student, I want attendance alerts so that I know when my attendance requires attention. | Low |
| US-20 | E6 | As a student, I want examination notifications so that I receive important exam information. | Medium |
| US-21 | E6 | As a student, I want result notifications so that I know when results are published. | Medium |
| US-22 | E7 | As an administrator, I want a student report so that student information can be reviewed efficiently. | Medium |
| US-23 | E7 | As an administrator, I want a performance report so that academic outcomes can be analyzed. | Medium |
| US-24 | E7 | As an administrator, I want a course report so that course enrollment information can be reviewed. | Low |

# 7. Acceptance Criteria and Definition of Done

Acceptance Criteria are measurable conditions used to decide whether a User Story is complete. A story is not considered Done simply because coding has started or a screen exists.

| User Story | Acceptance Criteria |
| --- | --- |
| US-01 Login | Login page loads successfully; valid users can log in; invalid credentials show an appropriate error; successful login redirects to the correct dashboard; session handling works. |
| US-05 Register Student | Required fields are validated; unique student identification is checked; valid records are saved; confirmation is shown; unauthorized users cannot create records. |
| US-06 Search Student | Search accepts approved criteria; matching records are displayed; no-match cases are handled clearly; results follow user permissions. |
| US-10 Assign Course | Authorized staff can select a student and course; duplicate enrollment is prevented; enrollment is saved successfully; updated enrollment can be viewed. |
| US-12 Record Attendance | Faculty can select course and lecture date; students can be marked present/absent; records are validated and saved; attendance can be viewed later. |
| US-13 View Attendance | Student sees only authorized attendance information; percentage is calculated correctly; course-wise information is clearly displayed. |
| US-15 Enter Marks | Authorized users can select the correct assessment; marks are validated; values are saved; invalid input produces an error message. |
| US-17 Calculate Grades | Approved grade rules are applied consistently; grades are generated from valid marks; calculation errors are prevented; output is stored for result processing. |
| US-18 View Result | Only approved results are displayed; students see only their own result; marks/grades are clearly presented; unavailable results are handled properly. |
| US-22 Student Report | Authorized users can generate the report; report contains required student information; output is readable and based on current validated data. |

## 7.1 General Definition of Done (DoD)

Acceptance Criteria are satisfied.

Feature is implemented and reviewed for logical correctness.

Required validation and error handling are included.

Appropriate unit or functional testing has been completed.

Role-based security rules are respected.

Documentation or backlog status is updated.

The Product Owner can verify the expected outcome.

No known critical defect prevents the feature from working.

# 8. Prioritized Product Backlog

The Product Backlog is prioritized according to business value, user importance, technical dependencies, MVP scope and implementation complexity.

| Rank | ID | Backlog Item | Epic | Priority | Release |
| --- | --- | --- | --- | --- | --- |
| 1 | US-01 | User Login | E1 | High | MVP |
| 2 | US-04 | Role-Based Access Control | E1 | High | MVP |
| 3 | US-05 | Register Student | E2 | High | MVP |
| 4 | US-06 | Search Student | E2 | High | MVP |
| 5 | US-10 | Assign Students to Courses | E3 | High | MVP |
| 6 | US-12 | Record Attendance | E4 | High | MVP |
| 7 | US-13 | View Attendance | E4 | High | MVP |
| 8 | US-15 | Enter Marks | E5 | High | MVP |
| 9 | US-17 | Calculate Grades | E5 | High | MVP |
| 10 | US-18 | View Result | E5 | High | MVP |
| 11 | US-02 | User Logout | E1 | High | MVP |
| 12 | US-09 | Add Course | E3 | Medium | MVP |
| 13 | US-07 | Update Student | E2 | Medium | MVP |
| 14 | US-08 | View Student Profile | E2 | Medium | MVP |
| 15 | US-11 | View Course Details | E3 | Medium | MVP |
| 16 | US-14 | Attendance Reports | E4 | Medium | MVP |
| 17 | US-16 | Update Marks | E5 | Medium | MVP |
| 18 | US-20 | Examination Notifications | E6 | Medium | Later |
| 19 | US-21 | Result Notifications | E6 | Medium | Later |
| 20 | US-22 | Student Report | E7 | Medium | MVP |
| 21 | US-23 | Performance Report | E7 | Medium | Later |
| 22 | US-03 | Password Reset | E1 | Medium | Later |
| 23 | US-19 | Attendance Alert | E6 | Low | Later |
| 24 | US-24 | Course Report | E7 | Low | Later |

# 9. Story Point Estimation

Story Points estimate relative effort, complexity, uncertainty and technical risk. They do not represent exact hours.

| Story Points | Meaning |
| --- | --- |
| 1 | Very Easy – small, low-risk change |
| 2 | Easy – simple implementation with limited dependencies |
| 3 | Moderate – normal development and testing effort |
| 5 | Difficult – multiple steps or dependencies |
| 8 | Very Difficult – significant logic, integration or uncertainty |
| 13 | Highly Complex – should normally be split before implementation |

| ID | Story | Points | Estimation Reason |
| --- | --- | --- | --- |
| US-01 | Login | 5 | Authentication flow and validation |
| US-04 | Role-Based Access | 8 | Security rules affect multiple modules |
| US-05 | Register Student | 5 | Validation and central data creation |
| US-06 | Search Student | 3 | Search and permission-based viewing |
| US-09 | Add Course | 3 | Standard validated data management |
| US-10 | Assign Students to Courses | 5 | Relationship and duplicate prevention |
| US-12 | Record Attendance | 8 | Course/date/student workflow |
| US-13 | View Attendance | 3 | Percentage display and authorization |
| US-15 | Enter Marks | 5 | Assessment validation and data handling |
| US-17 | Calculate Grades | 5 | Consistent academic calculation rules |
| US-18 | View Result | 5 | Approved result access and presentation |
| US-22 | Student Report | 5 | Data aggregation and report generation |

Planning Poker simulation: each story is discussed by the Scrum Team, complexity is compared with previously estimated work, and the final point value is agreed collaboratively.

# 10. Sprint Planning

The MVP is divided into four logical Sprints. Dependencies are handled early so later modules can use stable authentication and academic data.

| Sprint | Sprint Goal | Main Deliverable | Selected Stories |
| --- | --- | --- | --- |
| Sprint 1 | Secure Foundation and Project Setup | Authentication, RBAC, repository setup, basic interface and testing | US-01, US-02, US-04 |
| Sprint 2 | Student and Course Management | Student records, search, update, courses and enrollment | US-05, US-06, US-07, US-08, US-09, US-10, US-11 |
| Sprint 3 | Attendance and Academic Performance | Attendance recording, viewing, marks entry and grade processing | US-12, US-13, US-14, US-15, US-16, US-17 |
| Sprint 4 | Results, Reports and Release Readiness | Result access, basic reporting, notifications and final validation | US-18, US-20, US-21, US-22, US-23 |

# 11. Sprint Backlogs

## Sprint 1

Sprint Goal: Deliver a secure project foundation so users can authenticate and access only permitted functions.

| ID | Backlog Item | Points |
| --- | --- | --- |
| US-01 | Login | 5 |
| US-02 | Logout | 2 |
| US-04 | RBAC | 8 |

Sprint Tasks:

Initialize repository and project structure

Create login interface and validation

Implement secure session/logout flow

Define user roles and permissions

Test authentication scenarios

## Sprint 2

Sprint Goal: Create the central student and course data foundation required by academic workflows.

| ID | Backlog Item | Points |
| --- | --- | --- |
| US-05 | Register Student | 5 |
| US-06 | Search Student | 3 |
| US-07 | Update Student | 3 |
| US-08 | View Profile | 2 |
| US-09 | Add Course | 3 |
| US-10 | Assign Course | 5 |
| US-11 | View Course | 2 |

Sprint Tasks:

Create student data model

Implement student registration and search

Implement controlled updates and profile view

Create course management

Implement student-course enrollment

Perform validation and integration testing

## Sprint 3

Sprint Goal: Deliver core attendance and academic performance workflows.

| ID | Backlog Item | Points |
| --- | --- | --- |
| US-12 | Record Attendance | 8 |
| US-13 | View Attendance | 3 |
| US-14 | Attendance Report | 5 |
| US-15 | Enter Marks | 5 |
| US-16 | Update Marks | 3 |
| US-17 | Calculate Grades | 5 |

Sprint Tasks:

Create attendance workflow

Calculate and display attendance percentage

Create attendance report

Implement marks entry/update validation

Implement grade calculation

Test academic workflow consistency

## Sprint 4

Sprint Goal: Make approved results and essential reports available and prepare the MVP for review.

| ID | Backlog Item | Points |
| --- | --- | --- |
| US-18 | View Result | 5 |
| US-20 | Exam Notification | 3 |
| US-21 | Result Notification | 3 |
| US-22 | Student Report | 5 |
| US-23 | Performance Report | 5 |

Sprint Tasks:

Connect approved grades to result view

Create basic notification events

Generate student and performance reports

Complete end-to-end testing

Prepare Sprint Review demonstration

# 12. Scrum Board Development

The Scrum Board provides visible progress tracking. The board is updated during Sprint execution so the team can immediately see unfinished work and bottlenecks.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Password Reset | Add Course | Record Attendance | RBAC Security Tests | Repository Setup |
| Notifications | Update Student | Enter Marks | Login Validation | Login UI |
| Advanced Reports | Student Report | Calculate Grades | Attendance Tests | Logout |
| Course Report | Performance Report | Result View | Marks Validation | Student Search |

## 12.1 Board Rules

Every selected Sprint item begins in To Do.

Work moves to In Progress only when development starts.

A completed implementation moves to Testing.

Only items meeting Acceptance Criteria and the Definition of Done move to Completed.

Blocked work is discussed during the Daily Scrum.

# 13. Burndown Chart and Sprint Progress

A Burndown Chart tracks the amount of remaining work during a Sprint. For this mini-project, Sprint 1 is simulated using Story Points.

| Sprint Day | Ideal Remaining Points | Actual Remaining Points | Progress |
| --- | --- | --- | --- |
| Day 0 | 15 | 15 | Sprint starts |
| Day 1 | 13 | 13 | Repository setup and login work started |
| Day 2 | 11 | 12 | Login functionality completed |
| Day 3 | 9 | 10 | RBAC implementation progressing |
| Day 4 | 7 | 8 | Role permissions implemented |
| Day 5 | 5 | 6 | Security and validation testing |
| Day 6 | 3 | 3 | Defects fixed and documentation updated |
| Day 7 | 0 | 0 | Sprint Goal achieved |

## 13.1 Textual Burndown Representation

Remaining Story Points

Day 0  15  ███████████████

Day 1  13  █████████████░░

Day 2  12  ████████████░░░

Day 3  10  ██████████░░░░░

Day 4   8  ████████░░░░░░░

Day 5   6  ██████░░░░░░░░░

Day 6   3  ███░░░░░░░░░░░░

Day 7   0  ░░░░░░░░░░░░░░░

Interpretation: the actual line reaches zero by the final Sprint day. Any difference between ideal and actual remaining work is used to discuss risks, blockers and capacity during Scrum ceremonies.

# 14. Simulated Scrum Ceremonies

## 14.1 Sprint Planning

The team reviews the highest-priority Product Backlog items, checks dependencies and selects work that supports the Sprint Goal. Stories are estimated using Story Points and clarified with Acceptance Criteria.

## 14.2 Daily Scrum Simulation

| Team Member Focus | Yesterday | Today | Challenge / Impediment |
| --- | --- | --- | --- |
| Development | Completed login interface and validation | Connect authentication to role permissions | Role rules must be tested across modules |
| Testing | Prepared login test cases | Test invalid credentials and session behavior | Need stable test data |
| Scrum Master | Updated board and reviewed blockers | Facilitate progress discussion | Ensure blocked work is visible |
| Product Owner | Clarified expected dashboard access | Review RBAC acceptance criteria | Confirm role permissions |

## 14.3 Sprint Review

The team demonstrates working features, verifies acceptance criteria and collects feedback from the Product Owner and relevant stakeholders. Feedback can create new or changed backlog items.

## 14.4 Sprint Retrospective

After the review, the Scrum Team discusses process improvement rather than only product features. The team identifies what worked well, what created friction and one or more improvements for the next Sprint.

# 15. Sprint Review Report

| Review Item | Sprint 1 Result |
| --- | --- |
| Sprint Goal | Develop a secure project foundation |
| Completed Demonstration | Login, Logout and Role-Based Access Control |
| Stakeholders Represented | Product Owner, Scrum Master, Development/Testing |
| Acceptance Criteria Status | Verified for selected completed stories |
| Feedback | Keep error messages clear and ensure each role sees only authorized functions |
| New Backlog Consideration | Password recovery and additional audit features remain future work |
| Release Decision | Sprint Increment accepted after agreed testing and review |

Sprint Review Outcome: The Sprint produced a usable foundation that can support Student and Course Management in the next Sprint. The Increment is considered valuable because later academic modules depend on secure authentication and controlled access.

# 16. Sprint Retrospective Report

| What Went Well | What Challenges Occurred | Improvement Action |
| --- | --- | --- |
| Clear Sprint Goal kept the team focused. | RBAC affected multiple screens and required careful checking. | Define permission rules earlier before implementation. |
| Acceptance Criteria reduced ambiguity. | Testing required repeated role-based scenarios. | Prepare reusable test cases for each role. |
| Scrum Board made progress visible. | Dependencies created some sequencing issues. | Identify technical dependencies during Sprint Planning. |
| Small increments were easier to review. | Documentation updates can be forgotten during development. | Add documentation checks to the Definition of Done. |

## 16.1 Retrospective Commitment

For the next Sprint, the team will identify dependencies before selecting stories, prepare test data earlier and update documentation continuously instead of leaving it until the end of the Sprint.

# 17. Comparative Study of Agile Frameworks

| Framework | Core Approach | Strength | Suitable Context |
| --- | --- | --- | --- |
| Scrum | Time-boxed Sprints, roles and ceremonies | Clear incremental delivery and frequent review | Small to medium projects with evolving requirements |
| Kanban | Continuous flow and visual work limits | Excellent visibility and flexible workflow | Support, maintenance and continuous delivery |
| Extreme Programming (XP) | Strong engineering practices and frequent feedback | Improves code quality and technical discipline | Software teams needing intensive development practices |
| Lean Development | Remove waste and maximize value | Focuses on efficiency and continuous improvement | Processes requiring flow and waste reduction |
| Large-Scale Scrum (LeSS) | Multiple teams working on one product | Extends Scrum principles to larger teams | Large product with several Scrum teams |
| Scaled Agile Framework (SAFe) | Enterprise-level planning and coordination | Supports complex organizational alignment | Large enterprises and portfolios |
| Scrum@Scale | Network of Scrum teams | Scales Scrum while retaining team autonomy | Organizations growing beyond one Scrum Team |

## 17.1 Recommended Framework

Scrum is the most suitable primary framework for this Student Record and Academic Management Platform mini project. The project has a clear MVP, multiple dependent features and benefits from short feedback cycles. Scrum provides a simple structure for prioritizing User Stories, organizing Sprints, reviewing working increments and improving the process.

Kanban can still complement Scrum for visualizing tasks through the Scrum Board, while XP engineering practices can later improve code quality. However, Scrum is the best overall choice for the present project size and academic objective.

# 18. Project Timeline and Release Roadmap

| Phase / Sprint | Focus | Timeline | Release Outcome |
| --- | --- | --- | --- |
| Phase 1 | Product Discovery | Unit 1 | Business problem, stakeholders, personas, requirements and MVP |
| Phase 2 | Agile Planning | Unit 2 – Initial | Vision, roles, Epics, User Stories and backlog |
| Sprint 1 | Foundation Release | Week 1 | Authentication, logout and RBAC |
| Sprint 2 | Academic Records Release | Week 2 | Student and course management |
| Sprint 3 | Academic Operations Release | Week 3 | Attendance and marks/grades |
| Sprint 4 | MVP Release | Week 4 | Results, reports and release validation |
| Post-MVP | Continuous Improvement | Future | Notifications, advanced reports, analytics and additional integrations |

## 18.1 Release Roadmap

Release 0 – Product Discovery: requirements and product direction established.

Release 1 – Secure Foundation: users can authenticate and access authorized functions.

Release 2 – Academic Data Core: student and course records are centrally managed.

Release 3 – Academic Operations: attendance and marks workflows are operational.

Release 4 – MVP: approved results and essential reports are available for the main user groups.

## 18.2 Dependency Flow

Authentication & RBAC → Student Records → Course Enrollment → Attendance / Marks → Grades → Results → Reports / Notifications

# 19. Complete Agile Documentation Summary

| Required Deliverable | Status / Coverage |
| --- | --- |
| Agile Project Planning Report | Completed through Product Vision, Epics, Backlog and Sprint Planning. |
| Product Vision Document | Defined with objective, users, benefits, success criteria and constraints. |
| Scrum Team Structure | Product Owner, Scrum Master and Development Team responsibilities documented. |
| Scrum Roles and Responsibilities | Detailed responsibilities included. |
| Epic Documentation | Seven product Epics defined. |
| User Story Repository | Twenty-four User Stories created. |
| Acceptance Criteria Document | Key measurable criteria and Definition of Done documented. |
| Prioritized Product Backlog | Ranked by business value, user importance and MVP scope. |
| Story Point Estimation Sheet | Relative complexity estimates provided. |
| Sprint Planning Document | Four logical Sprints planned. |
| Sprint Backlog | Detailed story and task selection for each Sprint. |
| Scrum Board | Backlog workflow and movement rules documented. |
| Burndown Chart | Sprint 1 simulated progress tracked in Story Points. |
| Sprint Review Report | Sprint outcome and stakeholder feedback documented. |
| Sprint Retrospective Report | Lessons learned and improvement actions documented. |
| Agile Framework Comparison | Scrum, Kanban, XP, Lean, LeSS, SAFe and Scrum@Scale compared. |
| Project Timeline and Release Roadmap | Phases, Sprints and MVP release path documented. |

# 20. Conclusion and Submission Checklist

This Unit-2 Agile Mini Project transforms the Unit-1 product discovery work into a structured Agile execution plan for the Enterprise Student Record and Academic Management Platform. The same business problem, stakeholders, personas, requirements, Product Vision and MVP have been maintained throughout the project so that Unit 1 and Unit 2 remain fully connected.

The project is organized from high-level Epics into User Stories, measurable Acceptance Criteria, a prioritized Product Backlog, Story Point estimates and four planned Sprints. Scrum ceremonies, a Scrum Board, Burndown tracking, Sprint Review and Sprint Retrospective are also included to demonstrate practical Agile collaboration and continuous improvement.

The recommended Agile framework is Scrum because it supports incremental delivery, frequent stakeholder feedback and clear Sprint-based planning. The final roadmap provides a realistic path from product discovery to an MVP release and future improvements.

## Final Submission Checklist

☑ Agile Product Vision

☑ Scrum Team Structure and Roles

☑ Project Epics

☑ User Story Repository

☑ Acceptance Criteria

☑ Definition of Done

☑ Prioritized Product Backlog

☑ Story Point Estimation

☑ Sprint Planning

☑ Sprint Backlogs

☑ Scrum Board

☑ Burndown Chart

☑ Scrum Ceremonies

☑ Sprint Review Report

☑ Sprint Retrospective Report

☑ Agile Framework Comparison

☑ Project Timeline and Release Roadmap

☑ Complete Agile Documentation

END OF UNIT–2 AGILE MINI PROJECT